## Torbay Strategy Action Plan
Torbay Oral Health Action Strategy Action Plan Phase One: Jan 2025-Dec 26 (reviewed six monthly)
Priority Area | Action | Target Date | Partners | Milestones (green text where complete) | Further information | Status | Torbay Risk Log | National KPIs (incl LA data) | Local KPIs
Children & Young People (programmes, data & intelligence) | Supervised Toothbrushing
| Support delivery of extended ICB funded service under contract variation to IMD 7-10 | 2025-04-01 | Home Dental NHS Devon | Identify eligible settings for provider Extended delivery launches Q2 2025 | Review via 6 weekly Public Health/Home Dental meetings |  |  | OHS-3YR OHS-5YR OHS-6YR EXTR-019 | School & nursery uptake
| Work with Home Dental to see whether young carers can be included in service | 2025-06-01 | Home Dental NHS Devon | Confirmation of Home Dental capacity to extend Ascertain best service/support contacts and cohort numbers | Review via 6 weekly Public Health/Home Dental meetings |  |  | EXTR-019 | Numbers for cohorts monitored at 6 month intervals
Fluoride Varnishing
| Complete re-modelling based on dental nurse/dental hygienist community delivery models and alternative reduced/scope/enhanced targeting In preparation for national guidance | 2025-03-01 | NHS Devon, DCC & PCC | Obtain national guidance on release re recommended service models for FV Programmes Complete prospective re-modelling based on targeted provision - children on GA pathway | National guidance due FEB 25 |  |  | NA | NA
| Complete procurement of ICB funded FV service for Devon - minimum 12 months from release of guidance. Primary schools in ICB deciles 1-6. Anticipated live date March 26 | 2026-03-01 | NHS Devon, DCC & PCC | Service provision and procurement timeline based on results of action above | Torbay Procurement Team aware and on hold |  |  | NA | KPIs TBC in service specification
Water Fluoridation
| Scope potential for roll-out of water fluoridation in Devon | 2026 TBC | NHS Devon, DCC & PCC | Monitor progress of NE England pilot scheme and subsequent government actions regarding potential further roll out |  |  |  | OHS-3YR OHS-5YR OHS-6YR EXTR-019 | NA
First Dental Steps
| Support continued delivery of programme 25-26 including pathways for families into high street dentistry or the Community Dental Service | 2025-03-01 | NHS Devon, DCC & PCC, 019 Service, CDS Team | Confirm continuation of funding for 25/26 Ensure OHID are liaising with 019 Team to keep them fully up to date |  |  |  | OHS-3YR OHS-5YR OHS-6YR EXTR-019 | KPIs TBC based on ICB service spec and contract 25/26
Open Wide Step Inside
| Delivery of ICB funded service to primary schools in IMD deciles 1-6. | 2025-03-01 | NHS Devon, DCC & PCC | On-boarding to commence early in 2025 | Public Health funded delivery 24-25 academic year - 25/26 delivery builds on previous provision |  |  | OHS-3YR OHS-5YR OHS-6YR EXTR-019 | KPIs TBC based on service spec and contract 25/26
Extraction under GA Report
| Scope establishment of a Devon wide report using Plymouth model of existing delivery to assist with local targeting and best use of resources | 2025-06-01 | NHS Devon, DCC & PCC | ICB agrees funding/structure to create a regular Devon wide report separated into LA areas pending OHID capacity to support regional exercise |  |  |  | NA | NA
Children & Young People (specific population group outputs) | Children in care / SEND / young carers
| Establish MECC provision for children in care / SEND / young carers | 2025-06-01 | NHS Devon, PCC, DCC, Children's Services, Carer Support Teams | Develop oral health and dental access resources for health professionals working with children in care, SEND children (including learning disabilities) and young carers. Distribute when complete | Utilise 2025 NCMP Oral Health Guidance |  |  | EXTR-019 | NA
| SEND specific oral health content on Torbay Healthy Learning | 2025-06-01 | Public Health Torbay, CDS Team, primary schools | Review current content and update as required | Utilise 2025 NCMP Oral Health Guidance |  |  | EXTR-019 | NA
Adults (including vulnerable groups) | Mouth cancer
| Improve mouth cancer provision to help address levels of diagnosis and mortality in Torbay | 2025-12-01 | NHS Devon, DCC & PCC, CDS Teams | Ascertain current levels of community mouth cancer screening (via Community Dental Service) Implement a new screening programme for adults including specific vulnerable groups - people using drug, alcohol, homeless/rough sleeping and smoking cessation services . | ICB Steering Group agreed priority action |  |  | PHOF - Mouth Cancer Diagnosis and Mortality rates | NA
MECC (Making Every Contact Count
| Establish MECC provision for people using drug, alcohol, homeless/rough sleeping and smoking cessation services | 2025-12-01 | NHS Devon, DCC & PCC,CDS Teams Drug & Alcohol, Lifestyle and Homeless services | Develop resources/guidance regarding mouth cancer signs and symptoms, including advice on general oral health and dental access, for health professionals and the voluntary sector working with people using drug, alcohol, homeless/rough sleeping and smoking cessation services Distribute when complete |  |  |  | None available | Local TBC
Dental Provision for homeless/rough sleepers
| Create a new pathway for homeless/rough sleepers | 2025-12-01 | NHS Devon, DCC & PCC,CDS Teams Drug & Alcohol and Homeless services | Funding and model agreed for Devon wide pathway Service/pathway launches | ICB Steering Group agreed priority action. |  |  | None available | KPIs TBC based on ICB service spec and contract
Learning disabilities
| Improve oral health and dental access knowledge & awareness in the learning disability community/service support teams | 2025-12-01 | NHS Devon, DCC & PCC,CDS Teams. Adult Social Care | Develop bespoke advice and guidance on oral health and dental pathways for adults with learning disabilities and their carers/support workers Ascertain contact routes and cohort numbers via Adult Social Care Distribute when complete |  |  |  | None available | Local TBC
Food Banks
| Support people accessing foodbanks to improve their oral health, including oral health packs (toothbrushes and toothpaste) and information leaflets. | 2025-12-01 | NHS Devon, DCC & PCC, local food bank network | Ascertain current food bank network and best means of contact Scope costs and availability of oral health packs | Opportunity to amplify through ICB Steering Group Local/ICB funding not secured yet |  |  | None available | Local TBC
Devon wide Oral Health Promotion Service
| Scope potential to create a Devon wide Oral Health Promotion Team - providing targeted support across the life-course | 2025-09-01 | NHS Devon, DCC & PCC, CDS Teams | Scope the potential to disaggregate the oral health promotion funding of Community Dentistry Teams in Devon to potentially fund a Devon wide Oral Health Promotion Team to promote oral health throughout the lifecourse based on the outreach model currently being delivered in One Cornwall | ICB Steering Group agreed action - NHS Devon Hub / ICB Commissioners researching potential to amend CDS contract prior to renewal in Sept 25 via internal process |  |  | None available | Local TBC
Older Adults | Guidance for care homes and domiciliary care
| Improve current oral health and dental access advice and guidance for the sector | 2025-06-01 | Public Health, ICB, Adult Social Care | Promote available HIVE training platform content to sector Establish delivery scope in Torbay for the new joint SW ICBs Care Homes Oral Health training service and assist with local delivery/promotion | Joint ICB funding for training posts agreed DEC 24 |  |  | None available | Local TBC
| Support delivery of OHID Epi Survey for oral health in care homes | 2025-12-01 | Adult Social Care, OHID | Identify dip sample of care homes based on OHID eligibility in conjunction with Adult Social Care Communicate upcoming survey to the sector in Torbay. Complete Survey | Survey due mid/late 25. Results early 26. |  |  | OHS-Care Homes (due early 26) | NA
Torbay Oral Health Action Strategy Action Plan Phase Two Jan 2027-Dec 29 TBC
`

## Action Status & KPI Key
Action Status Key
Complete
On track
Behind schedule
Closed (incl. reason)
Not started
Action KPI Key
OHS-3YR | PHOF - OHID Epi Survey of 3 year olds (every 3 years)
OHS-5YR | PHOF - OHID Epi Survey of 5 year olds (every 3 years)
OHS-6YR | PHOF - OHID Epi Survey of 6 year olds (every 3 years)
EXTR-019 | PHOF - HES data, extractions under general anaesthetic
OHS-Care Homes | PHOF - OHID Epi Survey of Care Home Residents (every 3 years)