| Originated by: RLW | Date approved: | Revision No: | Filed: Shared drive |
| --- | --- | --- | --- |
| Meeting Title | Torquay Town Deal Project Board Meeting |  |  |
| Date/Time | 13th June 2025 |  |  |
| Venue | Board Room, Torquay Town Hall/Teams |  |  |
| Attendees | Vince Flower (VF) – Chair David Carter (DC) Cllr Chris Lewis (CL) Julie Brandon (JB) Susie Colley (SC) Tracey Cabache (TC) Jim Parker (JP) Callum McGinnis (CM) Laurence Frewin (LF) Rebecca Woolley (RLW) Minutes |  |  |
| Apologies | Cllr Steve Darling MP (SD) – Vice Chair Chris Bartlett (CB) Emma Falconer (EF) George Helmore (GH) Andrew Robertson (AR) Jack Thompson (JT) |  |  |

# MINUTES

| 1. | Welcome & Apologies: | ACTION |
| --- | --- | --- |
| 1.1 | VF welcomed everyone to the meeting and apologies were noted. Minutes from previous meeting approved. |  |

| 2. | Declaration of Interest | ACTION |
| --- | --- | --- |
| 2.1 | JB declared she runs a business in Fleet Walk. There were no other Declarations of Interest. |  |

| 3. | Gifts & Hospitality Register | ACTION |
| --- | --- | --- |
| 3.1 | There were no items to record on the Gifts & Hospitality Register. |  |

| 4. | Minutes of previous meeting | ACTION |
| --- | --- | --- |
| 4.1 | Carry Forward JB asked if any funding could be available to tidy up Fleet Street? CB will report progress on discussions around vired funding and see if any can be identified. 07/02 A Meeting was held and an alternative solution the bins and phone boxes is now being sought, more information to follow. 13/06 DC will share position at next mtg. | DC |
| 4.2 | Closed SD reported that discussions are on-going regarding NHS eye/opticians on our High Street. JP/SD to discuss further. 13.06 close, discussions on-going. |  |
| 4.3 | Closed SC reported that the RHS Britain in Bloom is coming to Torquay, Swisco has big plans for Fleet St and Market St. SD/DC to discuss further. 13.06 updates will follow as plans unfold. |  |
| 4.4 | Closed SD asked about the ITF funding around the cycle path. CB will share when the information is available. |  |
| 4.5 | Closed Former Debenhams/The Strand project: CB will add Planning to the future Highlight Report for future discussion. |  |
| 4.6 | Carry Forward JB asked if we could see the figures around the proposal for another hotel on the harbourside? 13.06 DC will cover this point at the next meeting. | DC |
| 4.7 | Carry Forward Ready for Work/Sector Pathways LF updated that the Sector Pathways had proved helpful for SDC and EF will get some case studies for sharing. | EF |

| 5. | Highlight Report | ACTION |
| --- | --- | --- |
| 5.1 | Union Square VF asked when the Town Board involvement will end (Mar26?). VF asked for an update for the board once DC has more information to share. | DC |
| 5.2 | Debenhams (Strand Land Assembly) The plans for this project will be bought to the board when they are available. |  |
| 5.3 | HPR Project is now complete, there are some outstanding issues being resolved. 13.06 ‘Lessons Learned’ report being prepared. |  |
| 5.4 | Pavilion The target date for completion of ‘opening up’ works is Spring 2026. There are sessions ongoing with local groups to visit and watch the works progress. |  |
| 5.5 | Edginswell Station This project is parked. |  |
| 5.6 | Cultural Landscapes The project is on-going and updates will follow. The Bay of Lights is planned for this year with funding from another source. |  |

| 6. | AOB | ACTION |
| --- | --- | --- |
| 6.1 | No AOB, next meeting 15th August 2025. |  |

Minutes recorded by:  Rebecca Woolley

Next Torquay Town Deal Board meeting:

15 August 2025

17 October 2025

19 December 2025